TRARALGON CENTRAL BUSINESS DISTRICT

SAFETY COMMITTEE

12 Month Action Plan 2016

This Traralgon CBD Safety Committee Action Plan was initially developed in response to the outcomes and discussions from the Safe Street Summits held in Traralgon in 2008 , 2009 and 2010 and the recommendations contained in the Safe Street Summit Reports and has been reviewed and updated annually.

The action plan has been developed by members of the Traralgon CBD Safety Committee and recognises that many stakeholders have an interest and role in maintaining safety within the streets of Traralgon. With this in mind, responsibility for driving action has been shared amongst stakeholders.

# 1.0 Community Engagement

| # Strategy | # Action | # Responsibility | # Budget in Place | # When | # Evaluation Measures | # Updates |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1 Engage with a range of stakeholders to receive information, data, and feedback to assist with the planning of future strategies and actions | Analyse the previous data collection to establish baseline data. | Latrobe City Council | Core function | By March 2017 | Extension consultation and engagement with a range of stakeholders along with future strategies and actions formed which are reflective of community feedback. |  |
|  | Conduct conversational surveys of all businesses within the Traralgon CBD | Latrobe City Council | Core function | Once per year in the first quarter |  |  |
|  | Conduct conversational surveys with residents whose property is within two streets from the CBD district radius. | Latrobe City Council | Core function | Once per year in the first quarter |  |  |
|  | Conduct conversational surveys with pedestrians, public transport users and other relevant stakeholders. | Latrobe City Council | Core function | Once per year in the first quarter |  |  |
|  | Distribute surveys with the Traralgon CBD newsletters | Latrobe City Council | Core function | Once per year |  |  |
| 1.2 Build on existing networks and organisations to deliver the community safety message. | Deliver Business Safety information sessions to business owners through the Traralgon Chamber of Commerce | Traralgon Chamber of Commerce in conjunction with Traralgon CBD Safety Committee | Nil required | At least twice yearly | Increased awareness of community safety messages identified through participant feedback from presentations. |  |
|  | Facilitate opportunities to promote the community safety message through existing networks or organisations | Traralgon CBD Safety Committee | Nil required | Ongoing |  |  |
| 1.3 Develop a quarterly newsletter for distribution to local businesses and general community | Create newsletters which promote the achievements and strategic projects being undertaken by the Traralgon CBD Safety Committee | Latrobe City Council | Core function | February, April, July and October. | Development and distribution of newsletters with positive feedback received. |  |
|  | Distribute newsletters to local businesses and encourage businesses to make these available to the general public from their shop counters. | Latrobe City Council and Traralgon Chamber of Commerce | Nil required | February, April, July and October. |  |  |
|  | Distribute Newsletter to Local Neighbourhood Watch and Safer Community Groups. | Victoria Police | Nil required | February, April, July and October. |  | Autumn Newsletter distributed |
| 1.4 Provide regular media articles on relevant CBD Safety issues and achievements. | Target diverse media outlets as appropriate including local papers, radio, internet, Facebook, magazines, TV etc. to capture those that are not residents of Traralgon. | Traralgon CBD Safety Committee | Nil required | Ongoing | Printing or delivery of at least four messages per year. |  |
| 1.5 Continue to Strengthen the Traralgon and District Liquor Accord | Seek from the Traralgon and Districts Liquor Accord committee the endorsement of this Action Plan and commitment to take action on identified safety strategies in collaboration with the Traralgon CBD Safety Committee. | Victoria Police and Traralgon and District Liquor Accord | Nil required | Ongoing | Harmonious and cooperative relationships between the Traralgon CBD Safety Committee and the Traralgon and District Liquor Accord and the recently established Latrobe City Liquor Accord |  |

# 2.0 Security Infrastructure and Lighting

| # Strategy | # Action | # Responsibility | # Budget in Place | # When | # Evaluation Measures | # Updates |
| --- | --- | --- | --- | --- | --- | --- |
| 2.1 Installation of CCTV security cameras in priority areas | Meet current commitments for installation of the cameras in high needs areas | Latrobe City Council | Core function through DOJ funding | Ongoing | An increase in crimes solved through the use of CCTV identified through Victoria Police crime statistics. Increased safety perception identified through conversational surveys. |  |
|  | Development of a publicity and media campaign to raise awareness of the operation of the cameras | Latrobe City Council | Core function |  |  |  |
|  | Keep up to date with current trends and public and political influences around the use of CCTV cameras | Traralgon CBD Safety Committee | Nil required | Ongoing |  |  |
|  | Receive regular reports of relevant data from Victoria Police to demonstrate the effectiveness of CCTV cameras | Victoria Police | Core function | Ongoing |  |  |
| 2.2 Where a need is identified, improve CBD lighting in line with CPTED principals | Review the state of the current CBD lighting against the CPTED principals through the conducting of a safety audit | Latrobe City Council | Core function | Ongoing |  |  |
|  | Consider funding opportunities within Councils capital works program budget | Latrobe City Council | Core function | Ongoing |  |  |
|  | Explore funding opportunities for lighting improvements from other sources | Traralgon CBD Safety Committee | Nil required | Ongoing |  |  |

# 3.0 Transport

| Strategy | Action | Responsibility | Budget in Place | When | Evaluation Measures | Updates |
| --- | --- | --- | --- | --- | --- | --- |
| 3.1 To maintain a Night Time Bus Service | Actively seek ways to promote the Night Time Bus Service so that patronage remains high | Traralgon CBD Safety Committee | Nil required | Ongoing | To have a Night Time Bus Service operating consistently until December 2016 |  |
|  | Advocate for funding to ensure the ongoing viability of the night time bus service | Traralgon CBD Safety Committee | Nil required | Ongoing |  |  |
| 3.2 To continue to improve the Traralgon CBD taxi ranks so that they operate effectively and provide a safe and secure location for people to access | Continue to work with the Taxi Industry to ensure that the taxi ranks operate effectively for all | Latrobe Valley Taxis and Traralgon CBD Safety Committee | Nil required and core function | Ongoing | Reduced crime or complaints arising from patrons using the taxi ranks identified through Victoria Police statistics and conversational surveys |  |
|  | Monitor all feedback to identify any safety issues which are emerging and consider appropriate measures to reduce or prevent the issues from occurring. | Latrobe City Council | Core function | Ongoing |  |  |
| 3.3 To provide safe street environments within the Traralgon CBD for all pedestrian traffic | Conduct a safety audit of the current Traralgon CBD for pedestrian and patron safety | Latrobe City Council and Victoria Police | Core function | Ongoing | A reduction in traffic and pedestrian accidents identified through Victoria Police statistics A reduction in the number of traffic infringements issued identified through Victoria Police statistics |  |
|  | Develop strategies to address any identified safety risks | Latrobe City Council, Victoria Police and Traralgon CBD Safety Committee | Nil required | By December 2016 |  |  |
| 3.4 To provide public and community transport options to meet community needs | Review the current public and community transport options to identify any potential gaps or opportunities | Latrobe City Council | Core function | Ongoing | Completion of review and presentation of recommendations. |  |

# 4.0 Utilising Safety Legislation and Police Resources

| Strategy | Action | Responsibility | Budget in Place | When | Evaluation Measures | Updates |
| --- | --- | --- | --- | --- | --- | --- |
| 4.1 Maintain high levels of Police presence particularly during peak periods | Undertake special targeted operations where necessary | Victoria Police | Core function | Ongoing | A reduction in the number of street offences identified through Victoria Police statistics |  |
|  | Maintain high levels of visual presence particularly foot patrols within venues and around the local streets both day and night | Victoria Police | Core function | Ongoing |  |  |
|  | Continue to undertake targeted drug operations | Victoria Police | Core function | Ongoing |  |  |
| 4.2 Utilise the powers under the Designated Entertainment Precinct legislation | Utilise 24hr and longer term exclusion orders to remove trouble makers from the Traralgon CBD | Victoria Police | Core function | As required |  |  |
|  | Regularly provide updated photo i.d. Exclusion Order list to members of the Traralgon and District Liquor Accord | Victoria Police | Core function | Monthly |  |  |
|  | Notify Traralgon Police Station if anyone known to be on an exclusion order is detected within the Traralgon CBD or trying to enter venues | Venue operators / Traralgon and District Liquor Accord | Core function | As identified |  |  |
| 4.3 Utilise the powers of the Traralgon and District Liquor Accord barred list | Accurately report incidents and fill out the appropriate paperwork to enable nomination of troublemakers to the liquor accord barred list to remove trouble makers from licensed venues | Traralgon and District Liquor Accord | Nil required | Ongoing | A reduction in the number of criminal behaviour offences occurring within the CBD and also within licensed premises identified through Victoria Police |  |
|  | Encourage all licensed venues (including clubs, restaurants and entertainment venues) to abide to the terms and conditions for people barred under the Liquor Accord | Venue operators and Traralgon and District Liquor Accord | Nil required | Ongoing |  |  |

# 5.0 Drugs

| Strategy | Action | Responsibility | Budget in Place | When | Evaluation Measures | Updates |
| --- | --- | --- | --- | --- | --- | --- |
| 5.1 Identify strategies that the Traralgon CBD Safety Committee could undertake in relation to the issues of drugs and safety | Conduct research to learn more about drug initiatives in other areas | Latrobe City Council | Core function | Ongoing | A reduction in the number of drug related criminal behaviour offences committed in the Traralgon CBD as identified through Victoria Police statistics |  |
|  | Invite Drug and Alcohol workers from locally relevant services or a Victoria Police specialist to attend a CBD Safety Meeting / Liquor Accord Meeting to give a presentation about trends and issues in the use of illegal drugs | Latrobe City Council or Victoria Police | Nil required | By December 2016 |  |  |
|  | Seek to secure Drug and Alcohol services to be operating within the Entertainment Precent on a regular basis | Traralgon CBD Safety Committee | Core function for some | Ongoing |  |  |